Overview:

A Communications Work Plan that aims to increase public awareness of the Dementia Friendly Communities proof of concept project in the local pilot communities. The Communications Plan supports the project’s goals to raise awareness of dementia within the wider community with the aim to reduce stigma associated with the disease, and to build community capacity and ensure supports are available for individuals to age-in-place and remain in the community for as long as possible.

Objectives:

- Awareness: Create public awareness of the Dementia Friendly Community project and raise awareness of dementia

- Information: Seek opportunities to educate and inform community about the Dementia Friendly Community initiatives, and the resources and supports available within the community

- Engagement: Create or leverage opportunities to engage with the community, to build community capacity and ensure supports are available for individuals to age-in-place and remain in the community for as long as possible

Strategies:

- Spokesperson: Identify a spokesperson to champion the Dementia Friendly Communities project, help to raise the profile and influence the community

- News: Identify relevant story angles that demonstrate impact in the community and pitch stories to the news media

- Television Broadcasting: Utilize community programming resources available to produce Public Service Announcement (PSA) and/or Community Programming for television broadcast

- Publications: Identify and utilize existing health and community publications to feature targeted stories

- Library Speaker Series: Develop partnerships with the libraries to host a speaker series about Dementia Friendly Community and relevant topics

- Community Outreach Presentations: Seek opportunities to present DFC information at schools, businesses and other services

- DFC Events: Identify opportunities to create and host events in the community if applicable

- Partner Events: Identify opportunities to be a part of existing events taking place in the community to leverage event logistics, promotion and access to a captive audience

- Digital / Website / Social Media: Develop an online presence using organization and partner websites and online channels to promote the DFC initiative, as well as inform and engage audiences

- Collateral: Produce collateral to promote awareness and provide information on key messages for the initiative

Evaluation / Measurement:

- Number of media stories

- Number of stories published in other local publications

- Number of events held

- Number of attendees at events

- Number of presentations given

- Collateral produced

Target Audiences:

Pilot Communities:

Audience Segments:

| - Community members directly impacted by dementia: - People living with dementia - Caregivers - Employers of person with dementia or caregivers | Purpose: To increase understanding of, and access to, resources and supports available to people living with and directly impacted by dementia in the community |
| --- | --- |
| - General community (indirectly impacted by dementia): - Residents: - Youth - Adults - Seniors - Primary Businesses: - Banks - Drug stores - Grocery stores - Services: - Restaurants - Transportation - Recreation facilities - Health services - Faith Centre - Schools | Purpose: To mobilize the general community (Group B) to be able to better support individuals living with or directly impacted by dementia (Group A) |

# Communications (Public Awareness) Work Plan

Strategy: Spokesperson Identify a spokesperson to champion the Dementia Friendly Communities project, help to raise the profile and influence the community

| Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Celebrity / Expert spokesperson | Spokesperson for: - TV/PSA - Media interest - Host or guest speaker for events - Other? |  | - Awareness - Information - Engagement | Pitch: Opportunity for a person with influence to join project, and make a difference in the community. Affected by dementia so message resonates on a personal level |  |  |  |  |

Strategy: News / Media Identify relevant story angles that demonstrate impact in the community and pitch stories to the news media

| Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Launch event press release | Press release: Calgary Herald CBC Metro News |  | - Awareness - Information |  |  |  |  |  |
| Funding announcement | Press release / Press conference: Print, TV, Radio |  | - Awareness - Information | Funding Announcement Angle to feature a person living with dementia / caregiver to talk about message of hope and impact |  |  |  |  |
| Radio |  |  | - Awareness - Information |  |  |  |  |  |

Strategy: Television Broadcasting Utilize community programming resources available to produce Public Service Announcement (PSA) and/or Community Programming for television broadcast

| Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Community Programming | Shaw TV / CBC |  | - Awareness - Information | Follow the story of a person/s living with dementia. Produce as a series to include current state / interim updates and final wrap-up. |  |  | Work with a media partner (such as Shaw or CBC) to provide video production and storyboard / storytelling expertise. Complimentary |  |
| Public Service Announcement | Shaw TV |  | - Awareness | What is a Dementia Friendly Community? Impact / First in Alberta. Highlight success of proof of concept project. |  |  | Shaw TV Complimentary production and broadcast time |  |

Strategy: Publications Identify and utilize existing health and community publications to feature targeted stories

| Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Internal publication | Newsletter |  | - Awareness - Information | DFC Overview. Project status and regular updates. Impact stories. Call to action to get involved. |  |  |  |  |
| External Publication | Annual Report |  | - Awareness - Information | DFC Overview. Project status and regular updates. Impact stories. Call to action to get involved. |  |  |  |  |
| Magazine Publications | Print and online magazine |  | - Awareness - Information |  |  |  | Seek community publications that are distributed in your target community |  |
| Alzheimer’s Society Annual Report |  |  | - Awareness - Information |  |  |  |  |  |
| Alzheimer’s Society Newsletter | Stakeholder Annual Report |  | - Awareness - Information |  |  |  |  |  |
| Local Seniors News Publication | Stakeholder Newsletter |  | - Awareness - Information | DFC Partnership story |  |  |  |  |
| Other stakeholder publications | Newspaper |  | - Awareness - Information |  |  |  |  |  |
| Community Newsletters |  |  |  |  |  |  |  |  |
| Community Recreation Centre Newsletter |  |  | - Awareness - Information |  |  |  |  |  |
| Local Community Guide |  |  | - Awareness - Information |  |  |  |  |  |

Strategy: Library Speaker Series Develop partnerships with Calgary Public Library and Okotoks Public Library to host a speaker series about Dementia Friendly Community and relevant topics

| Item/Tactic | Medium / Venue | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Public Library Speaker Series | Public Libraries in local community |  | - Awareness - Information - Engagement | Speaker Series title idea – Forget Me Not: How to be a Dementia Friendly Community |  |  |  |  |

Strategy: Community Outreach Presentations Seek opportunities to present DFC information at schools, businesses and other services

| Item/Tactic | Medium / Venue | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| School Presentation | High Schools Middle Schools |  | - Awareness - Information - Engagement |  |  |  |  |  |
| Business Presentation | Businesses |  | - Awareness - Information - Engagement |  |  |  |  |  |
| Services Presentation | Services |  | - Awareness - Information - Engagement |  |  |  |  |  |
| Agencies Presentation | Agencies serving senior population |  |  |  |  |  |  |  |
| Presentation | Banks, restaurants, etc. as identified in introduction section of this document |  |  |  |  |  |  |  |

BSF/DFC Events:

| Item/Tactic | Medium / Venue | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Town Hall | Tudor Manor |  | - Awareness - Engagement | Introduction of DFC proof of concept / Find out about current state and needs in community |  |  |  |  |
| Year in Review symposium | Event to share success after some progress has been made |  | - Information - Engagement - Recognition | Year in review: sharing key learnings from Y1 |  |  | Determine purpose (is this an event for internal stakeholders to engage, and/or a public event)? |  |
| Year in Review symposium II | TBD |  | - Information - Engagement | Year in review: sharing key learnings from Y2 |  |  | Determine purpose (is this an event for internal stakeholders to engage, and/or a public event)? |  |

Strategy: Partner Events Identify opportunities to be a part of existing events taking place in the community to leverage event logistics, promotion and access to a captive audience

| Item/Tactic | Medium / Venue | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Symposiums |  |  | - Awareness - Information - Engagement | Innovation in Dementia Care: Overview of DFC Proof of concept project |  |  | DFC Presentation + Expo Booth profiling |  |
| Seniors Fairs |  |  | - Awareness - Information - Engagement | Overview of DFC Proof of concept project: Get involved / Impact |  |  | Tradeshow Booths Educational sessions |  |
| Identify other stakeholder/partner Events, Conferences and Tradeshows |  |  | - Awareness - Information - Engagement | Overview of DFC Proof of concept project Get involved Other messages TBD |  |  |  |  |
| Trade and Lifestyle Shows | Tradeshow |  | - Awareness - Information - Engagement |  |  |  |  |  |
| Charity events |  |  |  |  |  |  |  |  |
| Seniors Resource Fair |  |  |  |  |  |  |  |  |
| Seniors Week Tea | Community event |  |  |  |  |  |  |  |

Strategy: Online Develop an online presence using organization’s website and partner websites and online channels to promote the DFC initiative, as well as inform and engage audiences

| Item/Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Website | Organization’s Website Stakeholder websites |  |  |  |  |  |  |  |
| Social Media | Twitter Facebook |  |  |  |  |  |  |  |

Strategy: Collateral Produce collateral to promote awareness and provide information on key messages for the initiative

| Item/Tactic | Medium | Target Audience | Objective | Key Message | Timing | Responsible | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trifold brochure |  |  | - Awareness - Information | Overview of Dementia Friendly Communities proof of concept brochure |  |  | Include funding logos |  |
| Fact Sheet |  |  | - Awareness - Information |  |  |  |  |  |
| Pop-up Banners |  |  | - Awareness |  |  |  |  |  |
| Swag | Pens Other items? |  | - Awareness |  |  |  |  |  |
| Education / Resource collateral | Print Web |  | - Awareness - Information - Engagement |  |  |  |  |  |